## Network diagram
A medium sized company - "Lofthus frukt og saft" located at Hardanger fjord in western Norway - are producing one of the best apple juices in Norway. It is a 100% pure natural product, without any sugar added or other additives of any kind.
Until now they were mostly present at the local market in western Norway, but they have ambitions to expand and find new markets. As a part of this process they need a new website. The main purpose for the website will be to promote and sell their products. Also, information about the company and their production processes will be an important part of the website.
You have been asked by "Lofthus frukt og saft" to create the online website, including all the necessary content (identity elements, articles, photos etc.). At this moment they have just a logo and a simple brand strategy without any visual assets to use in the website production.
hold det enkelt
maksimum 30 tasks
Time chart og money chart
Critical tasks
Meet the customer Lofthus
receive the logo, colours, fonts, photos, theme and any marketing material
confirm customer expectations: "key deliverables" versus "nice to have"
confirm the budget/cost and the deadline/time
Organise the work
Kickoff meeting
verify commitments from within own team (deliverables and time)
Designer
recreate electronic version of logo, font and colours
create website buttons
create style tile
submit style tile to customer, receive comments
make adjustments to styletile
make summary of each website page
Define User Interface for the website
Programmer
purchase domain with hosting
programming of website
Floating tasks
fieldwork
take photos of production, sales counters and happy customers
gather articles from media
meet the customer
Lofthus frukt og saft
receive the logo, colours, fonts, photos, theme and any marketing material
confirm customer expectations: "key deliverables" versus "nice to have"
confirm the budget/cost and the deadline/time
Organise the work
Kickoff meeting
verify commitments from within own team (deliverables and time)
Designer
Programmer
recreate electronic version of logo, font and colours
create website buttons
create style tile
submit style tile to customer, receive comments
make adjustments to styletile
make Design summary for each website page
Define User Interface for the website
purchase domain with hosting
programming of website
Fieldwork
take photos of production, sales counters and happy customers
gather articles from media

## GanttTime
| Time Chart |  |  |  | 2020-08-17 | 2020-08-25 | 2020-09-02 | 2020-09-10 | 2020-09-18 | 2020-09-26 | 2020-10-04 | 2020-10-12 | 2020-10-20 | 2020-10-28 | 2020-11-05 | 2020-11-13 | 2020-11-21 | 2020-11-29 | 2020-12-07 | 2020-12-15 | 2020-12-23 | 2020-12-31 | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05
| Task name | Duration | Start | End | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 1 | 2 | 3 | 4 | 5
Critical tasks
Meet the customer Lofthus |  | 2 days | 2020-08-17 | 2020-08-19 | bar: 2020-08-17
receive the logo, colours, fonts, photos, theme and any marketing material | bar: 2020-08-25 to 2020-09-02
confirm customer expectations: "key deliverables" versus "nice to have" | bar: 2020-09-10
confirm the budget/cost and the deadline/time | bar: 2020-09-18
Organise the work
Kickoff meeting | bar: 2020-09-26
verify commitments from within own team (deliverables and time) | bar: 2020-10-04
Designer
recreate electronic version of logo, font and colours | bar: 2020-10-12
create website buttons | bar: 2020-10-20
create style tile | bar: 2020-10-28 to 2020-11-05
submit style tile to customer, receive comments | bar: 2020-11-13 to 2020-11-21
make adjustments to styletile | bar: 2020-11-29 to 2020-12-07
make summary of each website page | bar: 2020-12-15 to 2020-12-23
Define User Interface for the website | bar: 2020-12-31
Programmer
purchase domain with hosting | bar: 2021-01-01
programming of website | bar: 2021-01-02 to 2021-01-05
Floating tasks
fieldwork
take photos of production, sales counters and happy customers | bar: 2020-09-10 to 2020-10-04
gather articles from media | bar: 2020-10-12 to 2020-11-13

## GanttCost
| Cost in Thousands of NOK | 2020-08-17 | 2020-08-25 | 2020-09-02 | 2020-09-10 | 2020-09-18 | 2020-09-26 | 2020-10-04 | 2020-10-12 | 2020-10-20 | 2020-10-28 | 2020-11-05 | 2020-11-13 | 2020-11-21 | 2020-11-29 | 2020-12-07 | 2020-12-15 | 2020-12-23 | 2020-12-31 | 2021-01-01 | 2021-01-02 | 2021-01-03 | 2021-01-04 | 2021-01-05 | sum
| Task name | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 1 | 2 | 3 | 4 | 5
Critical tasks
Meet the customer Lofthus |  | 34: 2 | 2
| receive the logo, colours, fonts, photos, theme and any marketing material | [23 empty] | 2 | bar: 35 to 36
| confirm customer expectations: "key deliverables" versus "nice to have" | [23 empty] | 1 | bar: 37
| confirm the budget/cost and the deadline/time | [23 empty] | 1 | bar: 38
0
Organise the work | [24 empty] | 0
| Kickoff meeting | [23 empty] | 1 | bar: 39
| verify commitments from within own team (deliverables and time) | [23 empty] | 1 | bar: 40
0
Designer | [24 empty] | 0
| recreate electronic version of logo, font and colours | 41: 2 | 2
| create website buttons | 42: 2 | 2
| create style tile | 43: 2; 44: 2 | 4
| submit style tile to customer, receive comments | 45: 2; 46: 2 | 4
| make adjustments to styletile | 47: 2; 48: 2 | 4
| make summary of each website page | 49: 2; 50: 2 | 4
| Define User Interface for the website | 51: 2 | 2
0
Programmer | [24 empty] | 0
| purchase domain with hosting | 1: 2 | 2
| programming of website | 2: 2; 3: 2; 4: 2; 5: 2 | 8
0
0
Floating tasks | [24 empty] | 0
fieldwork | [24 empty] | 0
| take photos of production, sales counters and happy customers | 37: 3; 38: 3; 39: 3; 40: 3 | 12
| gather articles from media | [23 empty] | 5 | bar: 41 to 45
| sum cost | 2 | 1 | 1 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2

## Risk Factors
Description of Risk | How likely /5 | How serious /5 | Risk Factor | Plan to make less likely | Plan to make less serious | Scores AFTER mitigation actions
Customer takes time to confirm styletile | 2 | 3 | 6 | speak directly with decision maker | continue based on info received | 1 | 3
Designer is too busy to take the job | 3 | 5 | 15 | find an alternative designer | follow Gantt strictly | 1 | 5